## Sheet1
Rough Build Model
Unlocking Art 1.0
Development and Testing
(does not include ongoing support)
Framed as a 4-person team: prototyper, pair programming duo (one with better UI skills and one with better database skills), and tester/QA
Monthly sprints
Sheldon, with others, writes user stories one sprint ahead of the prototyper (John)
Prototyper works one sprint ahead of the exteme programming duo
Prototype, with suggestions for changes at the sprint review, becomes the spec for the exteme programming duo and the story the tester implements for regression testing
Daily build, monthly sprint review (could be 2-week or 3-week sprints also, but estimates are for 4-week sprints)
Sprints are calendar sprints; time estimates assume 50% productivity after meetings, training, demos, sprint reviews, planning, etc.
Tracker | Module | Submodule | Type | Main Dev | Re-factor | Notes
C | Curation
C1 |  | Picture source #1 import | Functional | 0.5 | 0.2 | Import pictures and associated meta-data from an existing API
|  | Picture source #2 import | Functional | 0.5 | 0.2 | Import pictures and associated meta-data from an existing API
|  | Picture source #3 import | Functional | 0.4 | 0.2 | Import pictures and associated meta-data from an existing API
|  | Picture source #4 import | Functional | 0.4 | 0.2 | Import pictures and associated meta-data from an existing API
|  | Picture source #5 import | Functional | 0.4 | 0.2 | Import pictures and associated meta-data from an existing API
|  | Metadata src #1 import | Functional | 0.5 | 0.2 | Enrich metadata by using multiple sources (e.g. Wikipedia)
|  | Metadata src #2 import | Functional | 0.5 | 0.2 | Enrich metadata by using multiple sources (e.g. Wikipedia)
|  | Metadata src #3 import | Functional | 0.3 | 0.1 | Enrich metadata by using multiple sources (e.g. Wikipedia)
|  | Resize pictures to our standard resolution | Functional | 0.5 | 0.5 | Have pictures available in resolutions ready for transmission
|  | Metadata editor | Functional | 1 | 1 | Edit meta-data
|  | Assume all meta-data sources are English unicode |  | 0 | 0 | No foreign languages
|  | Handle videos | Future | 0 | 0 | No videos
|  | DMCA notice handler | Functional | 0.5 | 1
|  | Report module for rights owners | Functional | 0.5 | 0.5 | How many times an image is viewed, by who and for how long it appears on a display device and what type of device it is
|  | Report module for management | Functional | 0.5 | 1 | Statistics on what people do with the system (e.g.utilization)
|  | Stability / reliability report module | Functional | 0.5 | 0.5 | Crashes, error codes, etc. reporting
|  | Auto-viewlists (by property of database) | Functional | 1 | 1 | Automatically add new art to appropriate system viewlists based on database field entries
|  | Manual editing of viewlists | Functional | 1 | 0.5 | Create and edit manual system viewlists or override system viewlists
|  | User management | Future | 0 | 0 | Manually re-set passwords or disable users
|  | Statistics by user | Future | 0 | 0 | Usage and error statistics by user
|  | Device management | Future | 0 | 0 | Manage relationships between users and their devices manually
|  | Disable device | Functional | 0.25 | 0.15 | Be able to "turn off" service to a device
|  | Image search by meta-data | Functional | 0.5 | 0.2 | Simple, basic ability to find images
| Ticketing system | Track and manage bugs and error reports | Functional | 0.8 | 0.5 | Will use an existing system, but need to configure it and specify reports, etc. May be less if we can find a tracking service instead of tracking software.
| Database | Architecture and setup | Design | 0.5 | 0.5 | Architect and design database
|  | Technology choice | Trial | 0.5 | 0.5 | Choose and trial architecture for database
|  | Field definitions and extensibility | Implement | 0.5 | 0.5
|  | Backup & restore | Implement | 0.25 | 0.25 | Depends on what Amazon provides
|  | Backup & restore | Test | 0.25 | 0.25 | Test backup and restore of database
|  | Viewlist - basic | Functional | 0.5 | 0.25
|  | Viewlist - personal | Functional | 0.5 | 0.25
|  | Viewlist - sharing | Functional | 0.5 | 0.2
|  | Metadata for viewlists | Functional | 0.25 | 0.1
Server Application
|  | Load balancing | Future | 0 | 0 | Assume not needed for v1
|  | Thread dispatching | Functional | 0.5 | 0.2 | Queue and handle incoming transactions
|  | Roku registration, management, and logging | Functional | 1 | 1
|  | Android registration, management, and logging | Functional | 1 | 0.5
|  | iPhone registration, management, and logging | Functional | 1 | 0.5
|  | Display picture module (basic) | Functional | 0.5 | 0.5 | Re-sizes and delivers a picture or the picture's URL, and provides the very basic metadata
|  | Display metadata module | Functional | 1 | 0.5 | Displays user-selectable set of additional metadata
|  | Select viewlist support | Functional | 0.5 | 0.1 | Selects a viewlist
|  | System viewlist support | Functional | 0.5 | 0.5 | Responds to requests for next/previoius picture in a viewlist with the picture ID
|  | Progressive display picture module | Functional | 0.5 | 0.2 | Provides a JPG-like progressively-improving picture
|  | Send enlargeable data picture module | Functional | 0.5 | 0.2 | For local zoom
|  | Send zoomed picture module | Functional | 0.5 | 0.2 | for replicating zoomed images on another device
|  | Auto-advance (time-based) | Functional | 0.5 | 0.2 | Determines if devices are still conneccted to Unlocking Art and auto-advances through the viewlist
|  | Navigate by genre (or other non-viewlist) | Functional | 0.5 | 0.2
|  | Personal viewlist support | Functional | 0.5 | 0.5
|  | Shared viewlist support | Functional | 0.5 | 0.2
|  | "Like" functionality | Functional | 0.5 | 0.2
|  | User login | Future | 0 | 0 | Use only device to device mapping for 1.0
|  | Logging | Functional | 0.5 | 0.2
|  | Art statistics gathering | Functional | 0.5 | 0.2
Roku / TV Application
|  | Support one smart TV in addition to Roku | Functional | 2 | 1
|  | Roku dispatch loop and display (BrightScript) | Functional | 0.25 | 0.25
|  | Register and associate with server | Functional | 0.25 | 0.25
|  | Use Roku remote for <left> <right> in viewlist | Functional | 0.25 | 0.1
|  | Pre-cache pictures | Functional | 1 | 0.5
|  | Progressive display support | Functional | 0.25 | 0.1
|  | Display zoomed image | Functional | 0.5 | 0.25
|  | Meta-data overlay management | Functional | 0.25 | 0.1
|  | Keep-alive heartbeat to server | Functional | 0.25 | 0.1
|  | Display overlay data on remote button | Functional | 0.25 | 0.1
|  | Collect and report back viewtime by image | Functional | 0.25 | 0.1
Android Device
|  | Register and associate with server | Functional | 0.25 | 0.25
|  | Connect to a TV (one at a time) | Functional | 0.25 | 0.25
|  | Display an image | Functional | 0.25 | 0.25
|  | Pre-cache pictures | Functional | 1 | 0.5
|  | Progressive display support | Functional | 0.25 | 0.1
|  | Local zoom of image (gather more data) | Functional | 0.35 | 0.15
|  | Thread support and dispatch | Functional | 0.25 | 0.25
|  | Flip through images and select one for client from a viewlist | Functional | 0.5 | 0.25
|  | Flip to meta-data | Functional | 0.25 | 0.1
|  | Select system viewlist | Functional | 0.5 | 0.25
|  | Create and manage personal viewlist | Functional | 1 | 0.5
|  | Logging | Functional | 0.5 | 0.25
|  | Error reporting | Functional | 0.5 | 0.25
|  | Statistics collection | Functional | 0.5 | 0.25
|  | Image search by metadata | Future | 0 | 0
iOS device (iPad, iPhone)
|  | About the same as Android |  | 6.35 | 3.6
| Total |  |  | 43.5 | 27.3